## Event budget
Category | Item | Qty | Unit | Est. low | Est. high | Quoted | Actual | Notes
Venue | Room hire | 1 | day
Venue | Additional breakout rooms | 0 | day
Audio | PA system | 1 | day
Audio | Wireless microphones | 4 | each
Audio | Mixing console | 1 | day
Audio | Stage monitors | 2 | each
Video | Screen or LED wall | 1 | day
Video | Projector and lens | 0 | day
Video | Vision switcher | 1 | day
Video | Confidence monitors | 2 | each
Lighting | Stage wash | 1 | day
Lighting | Moving heads | 8 | each
Lighting | Lighting console | 1 | day
Staging | Stage deck | 1 | set
Staging | Lectern | 1 | each
Staging | Backdrop or set | 1 | set
Crew | Audio engineer | 1 | day
Crew | Video technician | 1 | day
Crew | Lighting operator | 1 | day
Crew | Show caller | 1 | day
Furniture | Seating | 0 | each
Furniture | Tables and linen | 0 | each
Registration | Registration desk | 1 | each
Registration | Badge printing | 0 | each
Catering | Catering per head | 0 | person
Catering | Catering staff | 0 | day
Logistics | Delivery and collection | 1 | trip
Logistics | Power or generator | 0 | day
Logistics | Parking and access fees | 0 | item
Contingency | Contingency at 10% | 1 | item
TOTAL
Variance (actual vs quoted)

## How to use
Event budget template — CueQuote
Delete rows you do not need. Set Qty to 0 rather than deleting if you might add it back.
Fill Est. low and Est. high first, from experience or market rates. This is the range you take into the room.
Replace estimates with Quoted as real supplier quotes arrive. Keep the estimate — the gap between estimate and quote is the most useful number you will have next time.
Actual is what you were invoiced. Variance shows where the budget moved.
Contingency at 10% is a starting point. Under 5% is optimism; over 20% usually means the scope is not settled yet.
Totals are formulas — they update as you type. If you insert rows, extend the SUM range.
cuequote.com